## Previous quote
Hi Steve,
Thank you for your proposal. How do you think you will fare with the more complicated labelling, and also the abstracting of information and its inclusion in legends (also the different coloured lifework showing various structural elements).
Peter
> On 25/06/2019, at 10:34 PM, steve taylor <matauranz@gmail.com> wrote:
>
> Peter Knight,
>
> As discussed Monday 24th June 2019.
>
> RFP for Otago Regional Council,
> Taieri Drains Survey 2019 in preparation by Peter Knight,GeomaticsNZ.
>
>
> Quote :
>
> Contracted work for GeomaticsNZ by
>
> Stephen Taylor ,
> Engineer,
> 497 South Rd.,
> DUNEDIN.
> M 022 571 9141.
>
>
>
> To deliver to GeomaticsNZ.
>
> Cross Section ,Bridge and Culvert Plotting to ORC standard as Autocad pdf plots one pdf file per section.
>
> Contract Rate $30.00 /hr.
>
> 8 hours per day $240.00/day
> 5 days per week for 4 weeks $4800.00 total.
>
> Data to be supplied at close of each field day by field crews.
>
> Data to be supplied as Excel files reduced to standard ORC format.
> Initial production at 10 sections per day.
>
> 8 hours at 10 sections 48min per section.
>
> Excess daily sections to be held over until field work slows down.
>
> Support for CHC GNSS survey equipment to be supplied as required.
>
> I will source a suitable laptop with i7 processor required for Autocad and GIS software.
>
>
> I have read the communications with Bickesh ,Engineer ORC regarding probable and possible numbers of sections , bridges and culverts and the example drawings supplied by ORC.
>
>
>
> Yours,
> Stephen Taylor.